## Sheet1
FERC Project No. 2009-018
Virginia Electric and Power Company, dba |  |  | 1 of the monitoring provisions
Dominion Virginia Power/Dominion North Carolina Power |  |  | 2 with the DFRTAC concerning results of the monitoring,
3 the results, agency comments, and licensee's response to agency comments
License Article 401. Commission Approval and Reporting |  |  | with the Commission
(1) Revised Plans and Design Drawing for Commission Approval
Schedule
Settlement Agreement
Article & Section No. | Plan or Facility | Implementation1 |  | Consultation2 | Filing3 | Methodology
FS2, 3.1-3.3, 3.5 & 3.7 | American Eel Distribution Study | Below dam studies: Q1-Q4 2005 - 2008 @ RR; Q1-Q4 2009 - 2013 @ Gaston. Above dam studies: Q3-Q4 2008, 2011, 2014 (at least), 2017, 2020, 2023 (at most) for RR; Q3-Q4 2013 (at earliest), 2016, 2019 (at least), 2022, 2025, 2028 (at most) for Gaston |  | Below dam studies: Q1 2005 - Q4 2009 for RR; Q1 2009 - Q4 2013 for Gaston. Above dam studies: 2008, 2011, 2014 (at least), 2017, 2020, 2023 (at most) for RR; 2013 (at earliest), 2016, 2019 (at least), 2022, 2025, 2028 (at most) for Gaston | Below dam studies: May 31, 2006; May 31, 2007; May 31, 2008; May 31, 2009 for RR; May 31, 2010; May 31, 2011; May 31, 2012; May 31, 2013 for Gaston Above dam studies: May 31, 2009; May 31, 2012; May 31, 2015 (at least); May 31, 2018; May 31, 2021; May 31, 2024 (at most) for RR; May 31, 2014 (at earliest); May 31, 2017; May 31, 2020 (at least); May 31, 2023; May 31, 2026; May 31, 2029 (at most) for Gaston | See Attachment 1A for below RR dam study. Others to be developed in consultation with DFRTAC.
FS2, 3.4 & 3.6 | Upstream Eel Facility Design | 2008 (or earlier) for RR; 2012 for Gaston |  | Q3 2008 (or earlier) for RR; Q3 2012 for Gaston | October 31, 2008 (or earlier) for RR; October 31, 2012 for Gaston | To be developed in consultation with DFRTAC.
FS2, 3.4 & 3.7 | Upstream Eel Passage Effectiveness Study | 2009 (or earlier) - 2012 (or earlier) for RR (and possibly 2010, 2011, 2015, 2016, 2020, 2021); 2013 (at earliest) - 2016 (or earlier) for Gaston |  | Q4 2009 - 2012 (or earlier) for RR (and possibly 2010, 2011, 2015, 2016, 2020, 2021); Q4 2013 (at earliest) - 2016 (or earlier) for Gaston | March 31, 2010; March 31, 2011; March 31, 2012; March 31, 2013 for RR (and possibly March 31 of 2011, 2012, 2016, 2017, 2021, 2022); March 31, 2014; March 31, 2015; March 31, 2016; March 31, 2017 for Gaston | To be developed in consultation with DFRTAC.
FS2, 3.8 | Downstream Eel Passage Evaluation Study | 2013 |  | 2013 | March 31, 2014 | Literature Review and evaluation of current Best Available Technology (including costs and determination of downstream passage efficiency criteria).
FS2, 3.9 & 3.10 | Downstream Eel Passage Facility Design | 2015 for RR; 2018 for Gaston |  | 2015 for RR; 2018 for Gaston | March 31, 2016 for RR; March 31, 2019 for Gaston | To be developed in consultation with DFRTAC.
FS2, 4.1.1.6 & 4.1.2.1 | Initial American Shad Trap & Transport Facility | 2006 (plan to be developed in 2005) to continue until more permanent facilities required |  | Q3 2006 and ensuing years as needed. | October 31, 2006 and ensuing years as needed. | Initial efforts to explore use of electrofishing and fishwheel to collect fish, beginning in 2005.
FS2, 4.1.1.7 & 4.1.2.2 | Downstream Shad Passage & Turbine Mortality Study for Post-Spawned Adults & Out-Migrating Juveniles | 2005 for literature review. 2006 for further study (if needed) |  | Q4 2005 for literature review. Q4 2006 for further study (if needed). | March 31, 2006 for literature review. March 31, 2007 for further study (if needed). | Literature review of passage studies at similar hydro stations to determine if mortality at RR and Gaston expected to exceed 7% for juveniles and 15% for post-spawned adults. Further studies to be developed in consultation with DFRTAC.
FS2, 4.1.2.1 & 4.1.3 | Adult Shad Telemetry Study | 2007 - 2009 (or earlier) |  | 2005 - 2010 (or earlier) | 2010-05-31 | To be developed in consultation with DFRTAC
FS2, 4.1.4, 4.2.3 & 4.3 | Trap/Sort/Transport Facility for Shad at Roanoke Rapids Dam (including designs, construction, engineering testing, schedule for operation, and effectiveness testing) | 2007 (at earliest) for beginning design. Constructed and operational by 2009 (at earliest). |  | 2007 (at earliest) for design, and as needed beyond 2007. | May 31, 2008 (at earliest) for designs, construction, engineering testing, schedule for operation, and effectiveness testing. Comment from DFRTAC: It may take more than two years to design the trap/sort/transport facility, have the FERC review completed, and construct the facility. | To be developed in consultation with DFRTAC
FS2, 4.3.12 & 4.3.13 | Downstream Passage Measures for Juvenile and Post-Spawned Adult Shad | Need to be determined by results of Turbine Mortality Study, and other studies (if required). Time to be determined based on adult and juvenile movement through reservoirs, and a population level approximating 20K adults in two years. |  | As needed. | To be determined in consultation with the Commission. | To be developed in consultation with DFRTAC, if needed.